## Full Inspection Plan
2026 AG Annual Inspection Plan [-- Planned Assets: OSI & Internal]
Category | Package# for Piping Or Asset# for vessels & TKs | Item | Last Insp Date | Planned Insp Date | Next Inspection Category | Priority? | Insp Scope & Remarks | UT Progress | Report Issued? | API Eval. Done? | KPC Updated Master Sheet? | KPC Sent to Concerned Deps? | Remarks
| TAFR-NA-NA-010 | STORAGE TANK, CRUDE OIL, CAPACITY: 1200 BBL, TAG: T28 | 2018-10-01 | 2024-10-01 | NSD/Internal |  | Inspected in 2018 & Repaired with internal Sacrificial anodes. Need to be included in RBI Plan
| TAFR-NA-NA-011 | STORAGE TANK, CRUDE OIL, CAPACITY: 1200 BBL, TAG: T45 | 2018-10-01 | 2024-10-01 | NSD/Internal |  | Inspected in 2018 & Repaired with internal Sacrificial anodes. Need to be included in RBI Plan
| VEFD-NA-001 | FLASH GAS SUCTION SCRUBBER, COMP.1842, PY-02, TAG: V-1842B | None | 2024-12-01 | OSI-ADV |  | Insulation in bad condition & shall be repaired. Before repair, defected insulation and Insulation around nozzles shall be stripped & checked by VT/UT for severity of Corr under insulation (CUI). | holding | holding
| VEGE-IR-0015 | FLASH GAS SUCTION PULSATION BOTTLE, COMP.1843, MFG: INGERSOLL RAND, TAG: PD-1843-03 | None | 2024-12-01 | OSI-ADV
| VESB-ROPERTJENKINZ-001 | FLASH GAS K.O. DRUM, MFG: ROPERTJENKINZ, TAG: V-1223 | 2017-12-01 | 2024-12-01 | OSI-ADV |  | Included in GP SD
Vessels & Tanks | SEPARATOR-IP-AG-GP | INTERMEDIATE PRESSURE SEPARATOR, TAG: V-1250 | 2020-11-01 | 2025-01-01 | SD/Internal |  | Included in GP SD
| SEPARATOR-COLD-AG-GP | COLD SEPARATOR, MFG: CONSTRUCTION METALLIQUES DE PROVENCE, TAG: V-1215 | 2017-12-01 | 2025-01-01 | SD/Internal |  | Included in GP SD
| VEGE-GRAZEBROOK-001 | METHANOAL STORAGE TANK, MFG: GRAZEBROOK, TAG: V-1229 | 2019-11-17 | 2025-01-01 | SD/Internal |  | Included in GP SD
| STABILIZER-TOWER | STABILIZER TOWER, MFG: CONSTRUCTION METALLIQUES DE PROVENCE, TAG: V-1101 | 2013-04-01 | 2025-01-01 | SD/Internal |  | Included in GP SD
| VESB-ROPERTJENKINZ-002 | STABILIZER GAS K.O.DRUM, MFG: ROPERTJENKINZ, TAG: V-1222 | 2019-07-03 | 2025-01-01 | SD/Internal |  | Included in GP SD
| HBDF-CORC-001 | STABILIZER REBOILER, MFG: CAIRO OIL REFINING COMPANY, TAG: H-1407 | 2014-09-01 | 2025-01-01 | SD/Internal |  | Included in GP SD
| VESE-ROPERTJENKINZ-001 | FRACTIONATOR FEED DRUM, MFG: ROPERTJENKINZ, TAG: V-1224 | 2021-05-30 | 2025-01-01 | SD/Internal |  | Included in GP SD
| VEGE-GRAZEBROOK-003 | FUEL GAS KOD V-1242, IR COMP. ENGINES, MFG: GRAZEBROOK, TAG: V-1242 | 2017-11-01 | 2025-01-01 | SD/Internal |  | Included in GP SD
| VEGE-PETROJET-001 | NEW COLLECTION VESSEL, TAG: 10-V-02 | 2020-12-01 | 2025-01-01 | SD/Internal |  | Included in GP SD
| VESB-PPI-005 | INLET SUCTION SCRUBBER, COMP.1854, MFG: PPI, TAG: V-1254 | 2019-01-01 | 2025-01-01 | NSD/Internal |  | 1-2019: Internal Insp. Done with applying DURMETAL + internal coating to bottom head + reducing SRV from 1000 to 600 psi. The interval extended from 5 to 6 yrs according to 1852 insp findings, so insp will be in 1-2025. See the remarks in temporary-repair tab regarding assuming the repair life of durmetal | Done | Done
| VESB-BSB-001 | FIRST STAGE SUCTION SCRUBBER, TAG: V-1261 | 2022-01-01 | 2025-01-01 | NSD/Internal |  | Not Internally Inspected Before (MH 20") - Vertical vessel, so will focus on bottom head corrosion. SOW During Internal Insp: Apply blasting, insp, repair by durmetal if any & painting
| VESB-PPI-001 | SECOND STAGE SUCTION SCRUBBER, TAG: V-1262 | 2022-02-01 | 2025-01-01 | NSD/Internal |  | Not Internally Inspected Before (MH 20") - Vertical vessel, so will focus on bottom head corrosion. SOW During Internal Insp: Apply blasting, insp, repair by durmetal if any & painting
| VEGE-NA-001 | INSTRUMENT AIR RECEIVER, SIZE: 3X9, CORROSION ALLOW 1/8", DESIGN: P/T:150 PSIG/150F, TAG: 10-1265 | 2020-12-01 | 2025-01-01 | NSD/Internal |  | Not Internally Inspected Before (MH 18") - Vertical vessel, so will focus on bottom head corrosion. SOW During Internal Insp: Apply blasting, insp, repair by durmetal if any & painting
| TAFR-WILLEBROEK-30K-001 | OIL STORAGE TANK 201, CAPACITY: 30090, MFG: G&G INTERNATIONAL WILLEBROEK BELGIUM, 1989, DIA: 73' 4 5/16'', PRESS: 8 IN. WATER, T: 150 F, H: 40', MATERIAL: ASTM A283 GR.C, TAG: T-08201 | 2021-07-01 | 2025-01-01 | SD/Internal |  | In 2011: The entire bottom plates (including annular plates) replaced & new painting applied on bottom & shell 1st course. According to API-653, Next Internal inspection shall be after Min 12 Yrs (i.e, 2023 so it's overdue) Required to avail outsource company to do MFL scan for TK bottom, followed by UT verification to identify where the soil corrosion is sever at underneath side, then repair will required. Planned SOW: Required cleaning, blasting, inspection (VT, PT, UT), repair if any, anodes & Painting. OSI done in 7-2021 which reavealed satisfactory condition; RL = 15 Yrs & next OSI in 7-2028. Asset Owner Note: Oil Specs will be affected during TK Outage, because only one TK-202 will be used as production & shipping. If Mgmt will accept off-specs, then insp shall be done in summer after OP SD
| TAFL-SUPERSTAR-11-01 | Kadesh Floating Tank NO: 1, MFG: Super Star, Edition: 11, SN: TK017 | Never | 2025-05-01 | OSI
| TAFL-SUPERSTAR-11-02 | Kadesh Floating Tank NO: 2 | Never | 2025-05-01 | OSI
| SEPARATOR-WD33-15-5-20K | VESSEL-SEPARATOR , MFG: PETROJET, CERTIFIED BY: PETROJET, CAPACITY: 20K BBL, TAG NO.V100D, BUILD YEAR: 2010, 3PH | 2024-07-01 | 2025-06-01 | OSI
| ?? | Instrument Air Receiver | 2024-06-01 | 2025-06-01 | OSI
| SEPARATOR-NEAG02-6K | VESSEL-SEPARATOR , MFG: PETROJET, CAPACITY: 6K BBL, CERTIFIED BY: PRESSON, SN: 1197-20, TAG NO.V100A, SERVICE: 3PH SEP. SWEET SER., BUILD YEAR: 2006 | 2024-07-01 | 2025-07-01 | OSI |  |  | Done | Done
| TAFR-NA-1.5K-006 | Shipping Tank No.3, For WD-33-15 Area | 2020-04-01 | 2025-07-01 | OSI |  |  | Done | Done
| TAFR-PETROMAINT-400-001 | STORAGE TANK, CRUDE OIL, MFG: PETROMAINT, CAPACITY: 400 BBL, SN: 2009-6/6, YEAR: 2009, MAX WORK PRESSURE: ATM PSIG AT 90 C,DESIGN PRESSURE : ATM, VOL: 400BBL, DESIGN TEMP: 90C,TAG: T-6601 | 2024-09-01 | 2025-09-01 | OSI |  | LOCATED IN WD-33-K | OUT OF SURVICE | OUT OF SURVICE
| TAFR-PETROMAINT-400-002 | STORAGE TANK, CRUDE OIL, MFG: PETROMAINT, CAPACITY: 400 BBL, SN: 2009-1/6, YEAR: 2009, MAX WORK PRESSURE: ATM PSIG AT 90 C,DESIGN PRESSURE : ATM, VOL: 400BBL, DESIGN TEMP: 90C,TAG: T-6602 | 2024-09-01 | 2025-09-01 | OSI |  | LOCATED IN MAHROOSA | Done | Done
| VESE-GULFCOAST-002 | STABILIZER SIDE SUCTION PULSATION BOTTLE, COMP.1842, TAG: PD-1842-01 | 2024-10-01 | 2025-10-01 | OSI |  |  | Done | Done
| VESE-GULFCOAST-001 | STABILIZER SIDE SUCTION SCRUBBER, COMP. 1842, PY-01, MFG: GULF COAST, TAG: V-1842 A | 2024-10-01 | 2025-10-01 | OSI |  |  | Done | Done
| TAFR-NA-5K-002 | STORAGE TANKS-FIXED ROOF, BRACKISH WATER, MFG:NA, CAPACITY:5000 BBL, LOCATION: RO-TANKS WATER MAKER, TAG: T-8302 | 2023-03-01 | 2025-10-01 | NSD / Internal |  |  | Done | Done
| TAFR-PETROJET-1K-028 | FRESH WATER TANK NO.1, AG WATER MAKER, 1000 BBL. OLD DESCRIPTION (TEMPORARY BRAKISH WATER TANK) | 2019-11-01 | 2025-11-01 | OSI |  |  | Done | Done
| VEGE-NA-001 | Instrument Air receiver-1265 of Compressor-1870 | 2020-12-01 | 2025-12-01 | Internal |  | Non-SD Item | OUT OF SURVICE | OUT OF SURVICE
| TAFR-NA-2.2K-002 | Shipping Tank No.2 , For WD-33-15 Area | 2021-08-01 | 2025-12-01 | OSI |  |  | Done | Done
| TAFR-NA-400-001 | TANK, DIESEL FUEL, WD-33-15 POWER STATION, MFG: NA, CAPACITY: 400 BBL, TAG: T-4101 | 2018-08-01 | 2025-12-01 | OSI
| VEGE-NA-044 | BOLT-12-2X Gas Boot | Check History | 2025-12-01 | OSI |  |  | Done | Done
| ?? | WD 33-K01X Gas Boot | Never | 2025-12-01 | OSI
|  | OP Skimmer |  |  |  |  | Inspected, Repaired & ATR Issued - Back to Service | Done | Done
|  | RZK Skimmer | [5 empty] | Done | Done
| VEGE-NA-020 | Oil Filter, For comp.1846 | 2022-01-01 | 2026-01-01 | OSI |  | No thickness reduction were found during last year, inspection to be performed after 2 years in order to attain corroson rate and perform remaining life calculations. SRV shall be adjusted with max value of 70 Psi, and name plate to be attached to the vessel including the design pressure of 70 psi in it. | Done | Done
| HEATER-101-AG | HEATER TREATER, TAG: H-20101 | 2025-09-01 | 2026-01-01 | OSI |  | Inspection windows cut in 12-2022 & 1st OSI done in 1-2023 & next OSI in 1-2026 | Done | Done
| SEPARATOR-102-AG-OP | SEPARATOR 102 , SEP 102, TAG: V-10102 | 2019-10-24 | 2026-02-01 | NSD / Internal |  | After major repair & painting (Anodes not confirmed), the vessel back to service in 4-2019. Since the vessel will be cleaned during planned GP SD in 2-2026, so it's opportunity for internal Insp in 2-2026 During Next Insp, the vessel will require cleaning, maybe blasting, insp, repair if any & painting, or the optimistic plan in 2-2026 to make durmetal at localized pitting, touch up painting and renew anodes | Done | Done
| VESB-IR-002 | SUCTION SCRUBBER OF 2nd STAGE, COMP.1840, MFG: INGERSOLL RAND, TAG: V-1840B | 2021-04-01 | 2026-04-01 | OSI |  | Safe MAWP until UT inspection equal to or less than : 675 psi | Done | Done
| SEPARATOR-104-AG-OP | SEPARATOR 104, MFG: NATIONAL TAN, TAG: V-12104 | 2023-07-01 | 2026-06-01 | OSI |  | Additional name plate attached Derated from 200 : 150 Psi. | Done | Done
| TAFR-PETROMAINT-750BBL-003 | DILUTION WATER TANK, CAPACITY :750 BBL, TAG: T-14001 | 2021-06-01 | 2026-06-01 | OSI |  | Received from KALABSHA, Painted & Internally CP Protected. (Previously used as a diesel Tank) Onstream Baseline-inspected in 6-2021, so there is no CR can be determined for CMLs As per API-653, if CR is unknown, so OSI UT Interval shall be 5 yrs, so next UT in 6-2026 (Int: 6-2031) | Done | Done
| NEAG02-GAS-BOOT | Gas Boot For NEAG-2 EPF | 2025-02-01 | 2026-06-01 | OSI |  | UT (on the same CMLs) will be done after 1yr from start servicing by 6-2026
| VEGE-HANOVER-NA-003 | Discharge Bottle, for 1846 Compressor, Mfg: The Hanover Company, SN: 9959, Size: 24", | 2021-07-01 | 2026-07-01 | OSI |  | Hot Item - Need thermal probes & couplants Need Cleaning from Turbines Team to start | Done | Done
| VEGE-PECO-001 | Fuel Gas Filter, For Comp.1846 | 2020-08-25 | 2026-07-01 | OSI |  |  | Done | Done
| VESB-NA-006 | GAS SCRUBBER, WD-33-15 MESS HALL | 2019-08-06 | 2026-08-01 | OSI |  |  | Done | Done
| VESE-HANNOVER-NA-001 | Separator, Three Phase Separator, Mfg: Hannover, SN: 03-100, OD: 48'', H: 15'0'', drawing No: D.486348110, Mfg Year: 2003, MDmt: 20 F at 275 Psi, MAWP: 275 @ 120 F | 2022-08-01 | 2026-08-01 | OSI |  | This vessel is 18" MH & will be used as mobile sep for well testing at MOP = 100 Psi. The vessel internally inspected in 8-2022, repaired, painted & 2 Al-anodes installed (10 Kg) at 6 O'clock position in water phase section, in order to provide min 12 Yrs future protection. Next planned OSI: 8-2026 (The date shall be updated to be 4 yrs after start servicing) Next Planned Internal Insp: (The date shall be updated to be 12 yrs after start servicing)
| VEGE-NA-026 | SUCTION DAMPER ( LEFT SIDE, LINE-2 ), FOR COMP.1845 | 2019-10-23 | 2026-11-23 | OSI |  |  | Done | Done
OP | PACK 07- 6 | 6- 10" Main drain line from concrete pond to sand pit | 2023-10-01 | 2025-04-01 |  |  | Joints #2 & #4 Should be replaced as they reached a critical thickness with Heavy Internal Corrosion - Hold As not sent in AI List (No Priority) | Done | Done
| PACK 07- 8 | 8- 3" discharge line of the elec. pumps of the concrete pond | 2022-02-01 | 2025-04-01 |  |  | Joints #2 & #4 Should be replaced as they reached a critical thickness with Heavy Internal Corrosion - Hold As not sent in AI List (No Priority) | Done | Done
| PACK 10 - 1 | 1-DAPAA offloading station | 2022-11-01 | 2025-04-01 |  |  | The underground Clamped section (at OP side) replaced & PL route changed in 2-2023. | Done | Done
| PACK 07- 5 | 5- 2" recovery line from the concrete pond to the skimmer | 2023-05-01 | 2025-05-01 |  |  | Replace the severly corroded Joints#8, 9, 10 by 2" Sch 80 before Aug-2023, then do UT as baseline inspection on the same joints after replacement date directly. Hold - Still Not Replaced | Done | Done
| PACK 12 - 4 | 04- 16” outlet gas stream line from sep.202 to 24” GL to GP | 2024-06-01 | 2025-06-04 |  |  | Base Line Inspection, Next UT after 1 year | Done | Done
| PACK 12 - 6 | 06- Two branches of 2 SRVs 12” *8” lines and 14'' outlet line to flare header | 2024-06-01 | 2025-06-06 |  |  | Base Line Inspection, Next UT after 1 year | Done | Done
| PACK 04A - 6 | 06=8" OIL LINE FM BOOSTER PUMPS TO TRANSFER PUMPS-sec1 | 2015 | 2025-08-01 |  |  | Done as per UT Team but Missed Reports | Done | Done
| PACK 04A - 7 | 07--oil line fm booster pumps to transfer pumps-section 2 | 2015 | 2025-08-01 |  |  | Done as per UT Team but Missed Reports | Done | Done
| PACK 04A - 8 | 08= discharge line of transfer pumps to shipping line | 2015 | 2025-08-01 |  |  | Done as per UT Team but Missed Reports | Done | Done
| PACK 06 - 8 | 08= 6'' SRV line from heater to flare header | 2020-11-01 | 2025-11-01 |  |  | Hold As not sent in AI List (No Priority) | Done | Done
| PACK 06 - 1 | 01= 10x18 gas line fm sep 102 to gas plant | 2016-01-01 | 2026-01-01 |  |  |  | Done | Done
| PACK 06 - 10 | 10 - 10'' GAS LINE FM KOD TO TURBINE & FLARE | 2016 | 2026-02-01 |  |  |  | Done | Done
| PACK 06 - 5 | 05= 2''x4'' Gas Line from Heater-Desalter to Flare | 2022-03-01 | 2026-03-01 |  |  |  | Done | Done
| PACK 06 - 17 | 17= 18" X 24" Associated Gas from OP to LLP Gas Compressors | 2022-03-01 | 2026-03-01 |  |  |  | Done | Done
| PACK 07- 1 | 1- 12" Collection header of the inlet skimmer | 2024-07-01 | 2026-03-01 |  |  | Replace joints 1A,1B,1C,3A,3B & 4 due to severe internal corrosion and pitting. After replacement,Next UT: March-2026 | Done | Done
| PACK 08 - 9 | 09= 2'' Outlet Line from Diluation Tank to Desalter | 2023-09-01 | 2026-05-01 |  |  | Joint #20 (Reducer), shall be replaced (Minimum thickness is less than required thickness). | Done | Done
| PACK 08 - 8 | 08= 4'' Manual drain line of DESALTER | 2024-01-01 | 2026-09-01 |  |  | Clamped Joints #30, #36 & #42 Shall be replaced Joints #34 & #38 Shall be replaced as they reached critical thickness with very high corrosion rate. In General: Due to Repeated Leaks and High Corrosion Rate, The most effective and reliable approach is to avoid future leakage by Replacing the Line with Non-Metallic Material (HDPE, ...etc.), Same like most drain systems at Oil Plant. | Done | Done
| PACK04B - 2 | 02=6'' recycle oil treatment line- section 2 | 2016-09-01 | 2026-09-01 |  |  | Clamped Joint#2 had been removed in 2022 as per OP info | Done | Done
| PACK 03 - 2 | 02--6'' oil line fm sep 103 to charge pumps | 2023-09-01 | 2026-10-01 |  |  | Permanently cut & remove the dead-leg (J#57 & 58) + Replace the corroded J#59 + Replace the clamed Tee-Joint#54. Note: The planned Action is to Replace the Tee-flanged section from J#46 to 64 including the leaked T-Joint#54 & J#59 + Add flushing point for the Dead-Leg J#57, 58. This Plan will be executed in 4-2025 | Done | Done
| PACK 08 - 3 | 03=2x3-drain line of separator 102 (Manual) | 2021-10-01 | 2026-10-01 |  |  |  | Replaced by HDPE | Replaced by HDPE
| PACK 02B - 1 | 01=12" x 14" OIL PROD LINE FM OLD MANIFOLD TO SEPARATOR # 101 | 2021-11-01 | 2026-11-01 |  |  | Clamped Section and the section covered by soil shall be replaced by new painted section above concrete support (AR#386926) | Done | Done
| PACK04B - 5 | 05=shipping oil line fm OPT-201-202 to booster pumps | 2016-11-01 | 2026-11-01 |  |  |  | OUT OF SURVICE | OUT OF SURVICE
| PACK04B - 6 | 06=8'' oil line fm new manifold to tanks - section 1 | 2016-11-01 | 2026-11-01 |  |  |  | OUT OF SURVICE | OUT OF SURVICE
| PACK04B - 4 | 04=08'' outlet line of OIL POWER TANK - | 2021-12-01 | 2026-12-01 |  |  |  | OUT OF SURVICE | OUT OF SURVICE
| PACK04B - 7 | 07--8'' oil line fm triplex to tanks-section 2 | 2021-12-01 | 2026-12-01 |  |  | Min. Corr. Allowance was 1.7 mm in 2015 - All other joints started from 2.7 mm CA | Done | Done
GP Process Piping | PACK 07 - 6 | INLET SEPARATOR - WATER -SIDE-GLASS PIPE | 2022-08-01 | 2025-03-01 |  |  |  | Done | Done
| PACK 12 - 2 | 02=10'' gas line fm Stab. tower to Stab. HEX - sec 2 (Rev.1& 2) | 2017-05-01 | 2025-03-01 |  |  | Hold - Need Very High Scaffold
| PACK 13 - 16b | 16b--alternative fuel gas line - sect. 2 | 2010-06-01 | 2025-06-01 |  |  |  | Done | Done
| PACK 03C - 1 | 01 = 8" TEST Gas LINE FM WELLS HEADER TO WSH-HDR-SECTION 1 | 2015-01-01 | 2025-08-15 |  |  |  | Done | Done
| PACK 05 - 5 | 05 = cond. line fm IP sep. to F.D.F. - sect.1 | 2023-12-01 | 2025-08-01 |  |  |  | Done | Done
| PACK 07 - 7 | INLET SEPARATOR - CONDENSATE -SIDE-GLASS PIPE | 2022-08-01 | 2025-08-01 |  |  |  | Done | Done
| PACK 09 - 10 | 10 = 10'' gas line fm REG KOD #1285 to Flare (Upstream LCV) & (Downstream LCV ) | 2019-12-13 | 2025-08-01 |  |  |  | Done | Done
| PACK 13 - 14 | 14--fuel line fm KOD 1242 to heaters | 2010-09-01 | 2025-09-01 |  |  |  | Done | Done
| PACK 01B - 2 | 02= 6''x8''x12'' Discharge Lines of Turbine units 1851,1852 to Amerya | 2024-12-01 | 2025-12-01 |  |  | J#17,18: UT Baseline done in 12-2024 & Due date in 12-2025. The remaining joints will be in 2-2033. | Done | Done
| PACK 03D - 3 | 03 = 12 disch. turbine header to Inlet SEP | 2022-09-01 | 2026-01-01 |  |  |  | Done | Done
| PACK 03 F - 1 | 01 = 4'' KPC LINE AT AG SIDE | 2011-01-01 | 2026-01-01 |  |  |  | Done | Done
| PACK 07 - 3 | Condensate Line - fm Inlet Sep. to Flare Header-LCV1 | 2022-08-01 | 2026-02-01 |  |  | Feb-2026: UT on joints Downstream LCV1 + J#5A of upstream LCV-1. Aug-2030: UT on the remaining joints of upstream LCV-1. | Done | Done
| PACK 09 - 9 | 09= 4" X 8" GAS LINE FROM REGENERATOR KOD TO DRYING PACKAGE | 2016-03-01 | 2026-03-01 |  |  |  | Done | Done
| PACK 14C - 11 | 11= SRVs lines from 1841 to flare header | 2023-03-01 | 2026-03-01 |  |  | Moh Tawfik Remarks: This line is under review by Ahmed Tawfik in 12-3-2023. I believe its name shall be modified to be 11= SRVs lines from 1841 to flare header (See DWG of Pack-14D/9). Also please add new row & name it as 12= SRVs Bypass Lines from 1841 to flare header (Dead-Legs) that already done before in dead-legs sheet, so that both items (SRV lines and their bypass) will be the complete flare system of 1841 .. I did this difficult matching in 1842 reports#9,10 for your references .. Amir Elghandour: I did the separation but in 1841 dead legs package, found only one deadleg which is BDV Bypass to Flare. Although while reviewing the report (11= SRVs lines from 1841 to flare header), it seems there's more than one bypass to flare. | Done | Done
| PACK 02F - 1 | 01 = 8''gl. fm well no.27 to WSH 1406 - sec.1 | 2016-06-01 | 2026-06-01 |  |  |  | Done | Done
| PACK 08 - 2 | 02= Drain line of In-KOD to Burn Pit Header | 2017-04-01 | 2026-06-01 |  |  |  | Done | Done
| PACK 11A - 7 | 07= HIGH - NORMAL LEVELMETER | 2021-07-01 | 2026-07-01 |  |  |  | Done | Done
| PACK 14C - 2A | 2A = (3x4) disch. line of comp. 1841 (3-rd stage) section 1 | 2023-02-01 | 2026-07-01 |  |  | Hot Item - Portion of line is insulated + under skid Next UT: July-2026: UT for the mentioned joints in evaluated report in addition the need to ask GP to remove the defected insulation from J#12 to J#16 & remove grating from J#10,11 for VI& UT. | Done | Done
| PACK 03 E - 3 | 03 = 8'' FLARE HEADER OF WSH & HP-TEST BRANCH | 2022-11-01 | 2026-08-01 |  |  | 2 Sections: Flare Header + Branch of H.P. & Test Header ===> Both shall be done in 8-2026
| PACK 14B - 5 | 05 = 2"x3" flare line system of 1st Stage of 1840 to flare header | 2023-08-01 | 2026-08-01 |  |  | Not hot - Scaffold needed | Done | Done
| PACK 14D - 4 | 04=3'' SRV Bypass Line of Stabilizer Suction Scrubber # 1842A | 2023-02-01 | 2026-09-01 |  |  | Weared portion replaced after 2018 with new painted section. This report is repeated in report#10 (same Pack#), so I prefer to separate item#10 into #10-1, #10-2, .. | Done | Done
| PACK 14D - 10 | 10= SRVs Bypass Lines from 1842 to flare header (Dead-Legs) | 2022-07-01 | 2026-09-01 |  |  | 9-2026: This is SRV bypass section#4, which is repeated (See Report#4; Pack-14D), so during next insp, please serarate this item into 4 reports (The repeated one is already separated) | Done | Done
| PACK 12 - 3 | 03 = gas line from Stabilizer HEX to Stab. Accumulator - sec 3 (Rev.1& 2) | 2011-12-01 | 2026-11-01 |  |  | This is Hot piping shall utilize hot couplant & probe, otherwise, to be done during GP shutdown
| PACK 01A - 6 | 10" G/L from Process to G/P COMP.( 1840-1841 )Sec.#2 | 2016-12-01 | 2026-12-01 |  |  | New description as per GP (10'' from LLP System to 1840 & 1841 suction lines). | Done | Done
| PACK 06 - 2 | 02=8''outlet line of test sep. to turbine - sect.2 | 2024-08-08 | 2026-12-01 |  |  |  | Done | Done
| Comp-1846 | 01 = 4x6x8'' GAS LINE FROM COMPRESSOR # 1846,47,48 TO FLARE HEADER | 2023-08-01 | 2026-06-01 |  |  | Newly Replaced/Added Section in 8-2023 SD - The whole Line is one Section now Found external Pitting 4 mm in Joint#44 Band-2 | Done | Done
| Comp-1846 | 05 = disch. line of comp. 1846 to IP separator & Flare | 2023-08-01 | 2026-05-19 |  |  | There is a modification at the end of th line as it became attached with the main discharge header of 1847 & 1848. Next inspection: shall specify this modifiaction and reflect this on the drawing. | Done | Done
MFDs | MFDs | Spyglass Oil MFD | 2023-03-01 | 2025-09-01 |  |  |  | Done | Done
| MFDs | WD 33-15 New Oil MFD | 2024-11-01 | 2025-11-01 |  |  | Baseline UT | Done | Done
| MFDs | WD 33-1 Oil MFD | 2023-05-01 | 2025-12-01 |  |  |  | Done | Done
| MFDs | WD-9B Oil MFD | NA | 2026-01-01 |  |  | Fed by WD-9B-1x Well | Done | Done
| MFDs | SWAG Water MFD | 2023-04-01 | 2026-02-01 |  |  |  | Done | Done
| MFDs | AG OP MFD | 2025-03-01 | 2026-03-01 |  |  |  | Done | Done
| MFDs | East Oil MFD | 2023-05-01 | 2026-09-01 |  |  |  | Done | Done
| MFDs | SAG Mini WATER MFD | 2019-12-02 | 2026-12-01
Trunk Lines | TLs | Trunkline-A from Shadow MFD to ARD MFD | 2022-06-01 | 2025-01-01 |  |  | Included in 2025 but not done | Done | Done
| TLs | TL# A from ARD Mini-MFD to tie-in with AG-141 (Sec-2) then to GP WSH-1 (Sec-3) | Never | 2025-02-01 |  |  | Overdue in Master Inspection Plan but not included in 2025 Inspection Plan | Done | Done
| TLs | 6" Trunk line from the well Mapel-1x to NEAG MFD then to Oil process | Never | 2025-04-01 |  |  | Overdue in Master Inspection Plan but not included in 2025 Inspection Plan | Done | Done
| TLs | 4" TL from Mini-HAWK MFD to Hawk MFD | Never | 2025-04-01 |  |  | Overdue in Master Inspection Plan but not included in 2025 Inspection Plan | Done | Done
| TLs | 6" PL from WD-33-1 Pig Launcher to Pig Receiver (~ 26 Km) - Sec#1 | Never | 2025-11-01 |  |  | Included in 2025 but not done
| TLs | Trunk line-A from SWAG old MFD to ARD Mini MFD | Never | 2025-12-01 |  |  | Included in 2025 but not done
| TLs | Trunk line-A from SWAG old MFD to ARD MFD | Never | 2025-12-01 |  |  | Included in 2025 but not done
| TLs | AG 121 Commingle Line FM AG (121, 131, 15, 130) TO ARD MFD | 2023-02-01 | 2026-02-01 |  |  |  | Done | Done
| TLs | Trunk line from NEW SWAG to SWAG OLD MFD - Header-A | 2024-05-01 | 2026-05-01 |  |  |  | Done | Done
| TLs | Trunk line from NEW SWAG to ARD MFD - Header-B | 2024-05-01 | 2026-05-01 |  |  |  | Done | Done
| TLs | Trunk line from header C at ARD MFD to Oil Process | 2023-07-01 | 2026-05-01
| TLs | Trunk line from header B at EAST MFD to Oil Process | 2024-05-01 | 2026-05-01 |  |  |  | Done | Done
| TLs | Trunk line A from SAG to HORST MFD | 2023-08-01 | 2026-06-01 |  |  |  | Done | Done
| TLs | Trunk line from header C at HORST MFD to Gas Plant | 2023-10-01 | 2026-06-01 |  |  |  | Done | Done
| TLs | TL# A from SPYGlass MFD to Mini-ARD MFD (Sec-1) | 2025-08-01 | 2026-08-01
| TLs | PL from 8" old Receiver to AG OP MFD (~15 Km) - Sec#3 | 2025-01-01 | 2026-08-01
| TLs | Trunk Line C from SAG MFD to HORST MFD |  |  |  |  | As Per Production & Mr. David Request to Review/Confirm replacements done and calculate MAWP for the line after replacement | Done | Done
Flow Lines | FLs | AG-44 | 2009-02-01 | 2025-02-01 | UT + VT |  | Min reading was 7 mm | Done | Done
| FLs | SWAG-05 | Never | 2025-02-01 | UT + VT |  |  | Out of Service | Out of Service
| FLs | WD-33-15-11 | Never | 2025-02-01 | UT + VT |  |  | Done | Done
| FLs | Apollonia - JDT 1-2 | Never | 2025-02-02 | UT + VT |  |  | Out of Service | Out of Service
| FLs | AG-52 | 2023-06-01 | 2025-02-03 | UT + VT |  |  | Done | Done
| FLs | AG-68 | Never | 2025-04-04 | UT + VT |  |  | Done | Done
| FLs | AG-130 X | Never | 2025-05-08 | UT + VT |  | Low WC% ~ 2% .. Low Corr Susciptibility | Done | Done
| FLs | SHADOW-E08X | Never | 2025-05-08 | UT + VT |  | High productivity : Oil production in 7-2023 is 1421 BBLS | Done | Done
| FLs | BOLT NAIL 3-1X | Never | 2025-05-08 | UT + VT |  | High productivity : Oil production in 7-2023 is 1068 BBLS | Out of Service | Out of Service
| FLs | HAWK-05ST | Never | 2025-05-08 | UT + VT |  | High productivity : Oil production in 7-2023 is 652 BBLS | Done | Done
| FLs | WD-33-21 | 2020-06-05 | 2025-06-05 | UT + VT
| FLs | AG-158 | 2024-07-01 | 2025-07-01 | UT + VT |  |  | Done | Done
| FLs | AG-65 | Never | 2025-07-01 | UT + VT |  | Low WC% ~ 2% .. Low Corr Susciptibility | Done | Done
| FLs | Shadow-W02 | 2025-01-01 | 2025-07-08 | UT + VT |  | Close Monitoring | Done | Done
| FLs | MONTEZOUMA-1X | 2023-11-01 | 2025-08-01 | UT + VT |  | Non-Std. Road Crossing shall be replaced by Standard ones. | Out of Service | Out of Service
| FLs | PACIFIC-3 | 2025-02-01 | 2025-08-01 | UT + VT |  | Close monitoring on well head connection (first 8 joints) due to high erosion-corrosion rate. | Done | Done
| FLs | WD-09-A03 | 2024-09-01 | 2025-09-01 | UT + VT |  |  | Done | Done
| FLs | OLYMPIC-01X | 2023-11-01 | 2025-11-01 | UT + VT |  | Non-Std. Road Crossing shall be replaced by Standard ones. Note: In 10-2023, Olympic 1x FL was handling the prod of new well Montezoma-1x. | Done | Done
| FLs | WD-33-15-5 | 2016-12-26 | 2025-12-01 | UT + VT |  |  | Done | Done
| FLs | AG-131 X (Operated by Gas lift) | 2023-10-01 | 2026-08-01 | UT + VT |  |  | Done | Done
| FLs | AG-41 | 2025-02-01 | 2026-02-01 | UT + VT |  |  | Done | Done
| FLs | EBED-A1X | Never | 2026-02-01 | UT + VT |  |  | tubing material | tubing material
| FLs | Pacific-02X | 2016-12-23 | 2026-12-01 | UT + VT |  |  | Out of Service | Out of Service
| FLs | Mahrousa-D01X | 2024-07-01 | 2026-04-01 | UT + VT
| FLs | NAG-1 to E-MFD | 2025-05-01 | 2026-05-01 | UT + VT |  |  | Done | Done
| 4 | SHADOW-E03 | 2025-12-01 | 2026-12-01 | UT + VT
| FLs | SHADOW-W01X | 2025-07-01 | 2026-07-01 | UT + VT |  |  | Done | Done
| FLs | WD-33-15-4 WIW | 2024-09-01 | 2026-05-01 | UT + VT
| FLs | WD-33-V-5 | Never | 2026-01-01 | UT + VT
| FLs | WD-09-B01X | 2025-02-01 | 2026-02-01 | UT + VT |  |  | Done | Done
EPF | Mahrousa | Line fm Test unit to TKs | 2024-09-01 | 2025-09-01
|  | Line FM TKs to booster Pumps | 2024-09-01 | 2025-09-01
|  | Inlet line to main shipping pumps | 2024-09-01 | 2025-09-01
|  | Outlet line from main shipping pumps | 2024-09-01 | 2025-09-01
| WD 33-15 | Need Site Visit to Review Changes, Update the list & Determine the plan |  | 2025-07-01
| WD 33-1 | Need Site Visit to Review Changes, Update the list & Determine the plan |  | 2025-07-01
| Bolt Area | Need Site Visit to Review Changes, Update the list & Determine the plan |  | 2025-10-01
Un-Planned | TLs | Trunk line D from SAG to ARD MFD |  |  | UT + VT | yes add | take check points after and befor new clamp | Done | Done
|  | 1.5''LCV-10 DRAIN LINE(UNION LEAK |  |  | UT + VT | yes add | take check points to determine the cutting point | Done | Done
|  | WD-9A9 |  |  | UT + VT | yes add |  | Done | Done
|  | 6'' FM COM 1842 to AMRYA suction (SD item) |  |  | UT + VT | yes add |  | Done | Done
|  | 7 cutting locations in gas plant |  |  | UT + VT | yes add |  | Done | Done
|  | Trunk line B from SAG to Horst & GP |  |  | UT + VT | yes add | VT & UT | Done | Done
|  | Trunk line F from SAG to Horst &GP |  |  | UT + VT | yes add | VT & check in replacement Joints | Done | Done
|  | Trunk line D from Horst to GP |  |  | UT + VT | yes add | VT & UT | Done | Done
|  | 6'' Trunk line C from SAG-MFD to ARD MFD - Header C |  | 2026-08-01 | UT + VT | yes add | ut & Vt(take check points befor new clamp) | Done | Done
|  | 6'' Trunk line from SAG-MFD to ARD MFD - Header D |  |  | UT + VT | yes add | VT & UT | Done | Done
|  | TL-A from Spyglass MFD to Mini-ARD MFD to GP (WSH-1) |  |  | UT + VT | yes add | VT & UT | Done | Done
|  | Trunk line from header G at horst MFD to GP |  |  | UT + VT | yes add | VT & UT | Done | Done
|  | 0 cutting location in gas plant |  |  | UT + VT | yes add | VT & UT | Done | Done
|  | HAWK-03 |  |  | UT + VT | yes add | VT & UT | Done | Done
| Vessels & Tanks | BRAKISH WATER TANK |  |  | UT + VT | yes add | BOTTOM INSPECTION | Done | Done
|  | Gas Boot A came from beni suef |  |  | UT + VT | yes add | VT & UT &PT | Done | Done
|  | Gas Boot B came from beni suef |  |  | UT + VT | yes add | VT & UT &PT | Done | Done
|  | Gas Boot 201 |  |  | UT + VT | yes add | VT & UT | Done | Done
|  | Gas Boot 202 |  |  | UT + VT | yes add | VT & UT | Done | Done
|  | 4 welded lifting lugs at GP |  |  | PT + VT | yes add | VT &PT | Done | Done
|  | LP Separator |  | 2026-08-01 | UT + VT | yes add | VT &uT | Done | Done
|  | skimmer 33-15 |  | 2026-09-10 | UT + VT | yes add | VT &ut | Done | Done
|  | separator (203) 33-1 |  | 2026-09-10 | UT + VT | yes add | VT &ut & internal inspection | Done | Done
| flow line | AG 119 |  |  | UT + VT | yes add | take check points after and befor new leakege | Done | Done
|  | OLYMPIC-N1X |  |  | UT + VT | yes add | VT & UT | Done | Done
|  | AG43 |  |  | UT + VT | yes add | VT & UT | Done | Done
|  | AG 83 |  |  | UT + VT | yes add | VT & UT | Done | Done
|  | NEAG #4 |  |  | UT + VT | yes add | VT & UT | Done | Done
|  | AG #93 |  |  | UT + VT | yes add | VT & UT | Done | Done
| OP | 6" drain line from tank 201& 202 to burn pit |  |  | UT + VT | yes add | VT & UT | Done | Done
|  | 24" new flare line from oil process to flare head |  |  | PT + VT | yes add | VT & UT | Done | Done
|  | SAG Line-B from GP Fence to OP [TL-B from ARD (at GP fence) to OP] |  |  | PT + VT | yes add | VT & UT | Done | Done
| GP | GPC LINE |  |  | UT + VT | yes add | VT & UT | Done | Done
|  | Bapetco HP To Gas Plant |  | 2026-08-01 | UT + VT | yes add | VT & UT | Done | Done